# Quest Explorer: Kanban Timeline

HTML and CSS Portfolio Project · Track B, Adventure Pack, Bonus Feature 2

This plan uses the 14-day core schedule plus buffer Days 15-17 as a work sequence, not calendar dates. The published proposal and delivery deadlines stay authoritative. The team is Arjun Baskar and Yasmine Anderson.

## How the board works

| Column | Meaning | WIP limit |
| --- | --- | --- |
| Backlog | Every task on this plan, not yet scheduled | none |
| To Do | Scheduled for the current phase | none |
| In Progress | Someone is actively working on it | 1 card per person |
| Review / QA | Finished, waiting for a teammate to check it | 3 cards |
| Done | Meets the card's definition of done | none |

Rules:

- Only move a card to Done after a teammate (not the author) has checked it.

- Keep one card per person In Progress. Finish before starting the next.

- A card should take at most half a day. Split anything bigger.

- Every card gets a Git commit that names it, for example Add route timeline (#12).

- From Day 15 on, add no new features. Only bug fixes, polish and presentation prep.

Suggested labels: layout, components, css-motion, a11y, content, bonus, docs, testing, bug.

## Roles

- Arjun Baskar: layout, navigation, content, repository and final release

- Yasmine Anderson: components, motion, accessibility, the bonus feature and its documentation

Both members review each other's work and make commits. Each person leads their areas above but must be able to explain all of the code.

## Starting point

A first draft of all four pages and styles.css already exists. That changes the plan in an important way: early days are for reading, understanding and personalizing the code, not writing it from zero. Each person must be able to explain their area during grading, so reading time is built into the schedule.

## Phase 1: Plan + Structure (Days 1-3)

| # | Card | Label | Owner | Est. | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 1 | Confirm track, extension pack and bonus feature | docs | Both | 1 h | Choices match the signed proposal |
| 2 | Create GitHub repo, .gitignore and folder structure (css/, images/) | docs | Arjun | 1 h | Both members can clone and push |
| 3 | Set up this Kanban board and add all cards | docs | Yasmine | 1 h | Cards, labels and WIP rules visible |
| 4 | Read through index.html and world-map.html; note one question per section | layout | Arjun | 2 h | Questions posted to the team |
| 5 | Read through mission.html and team.html | bonus | Yasmine | 2 h | Questions posted to the team |
| 6 | Read through styles.css (variables, cards, animations) | css-motion | Yasmine | 2 h | Can explain each section aloud |
| 7 | Open every page in a browser and list defects | testing | Both | 1 h | Defect list added as cards |
| 8 | Draw wireframes for all four pages (paper is fine) | layout | Arjun | 2 h | Photos stored in docs/ |
| 9 | Decide your own palette, fonts and world name | content | Both | 2 h | Design decisions written in README |

Checkpoint at end of Day 3: repo works, board is live, everyone has read the whole code once.

## Phase 2: Layout + Components (Days 4-7)

| # | Card | Label | Owner | Est. | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 10 | Review semantic structure and heading order on every page | a11y | Yasmine | 2 h | One h1 per page, logical order |
| 11 | Tune the Grid layout of the world map | layout | Arjun | 3 h | Regions reflow at 360, 768, 1024 and 1440 px |
| 12 | Refine shared header and navigation | layout | Arjun | 2 h | Same nav on all pages, current page marked |
| 13 | Finalize card, button and badge components | components | Yasmine | 3 h | Used consistently on all four pages |
| 14 | Add missing small-screen breakpoint rules | layout | Arjun | 2 h | No horizontal scrolling at 360 px |
| 15 | Build the mission page route steps | components | Yasmine | 3 h | Step list matches the proposal |
| 16 | Add a visible-focus pass for every interactive element | a11y | Yasmine | 2 h | Keyboard-only tab-through succeeds |
| 17 | Write the real content for the world map regions | content | Arjun | 3 h | No placeholder text left on map page |

Checkpoint at end of Day 7: all four pages are responsive and use the shared components.

## Phase 3: Styling + Motion (Days 8-11)

| # | Card | Label | Owner | Est. | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 18 | Apply your chosen palette and fonts through CSS variables | css-motion | Arjun | 3 h | Colors changed in :root only |
| 19 | Tune hero visual and the lantern animation | css-motion | Yasmine | 3 h | Looks good and respects reduced motion |
| 20 | Review all animations (at least three) and the reduced-motion fallback | css-motion | Yasmine | 2 h | Animations stop with the OS setting on |
| 21 | Complete the Adventure Pack route timeline states | components | Arjun | 3 h | Done, current and locked states are clear in text, not color only |
| 22 | Build the Recommendation Engine UI cards with confidence labels | bonus | Yasmine | 3 h | Three suggestion cards with hints |
| 23 | Add the explainability hints and the simulation notice | bonus | Yasmine | 2 h | Notice says suggestions are simulated |
| 24 | Check text and UI contrast with a contrast tool | a11y | Arjun | 2 h | All text meets WCAG AA, fixes committed |
| 25 | Write real missions and links between pages | content | Arjun | 3 h | Every link goes somewhere sensible |
| 26 | Peer review of all styling cards | testing | Both | 2 h | Review notes added as comments |

Checkpoint at end of Day 11: design is final, extension pack and bonus feature are integrated into the main flow.

## Phase 4: QA + Portfolio Packaging (Days 12-14)

| # | Card | Label | Owner | Est. | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 27 | Run the W3C HTML validator on all pages | testing | Arjun | 1 h | Zero errors, or documented exceptions |
| 28 | Run the W3C CSS validator | testing | Yasmine | 1 h | Zero errors, or documented exceptions |
| 29 | Run Lighthouse accessibility checks | a11y | Yasmine | 2 h | Score recorded in README |
| 30 | Responsive test at 360, 768, 1024 and 1440 px (plus one real device if possible) | testing | Both | 2 h | Results table in README |
| 31 | Usability test with at least three peers, using three tasks | testing | Both | 3 h | Task table with notes saved |
| 32 | Write 3+ bonus feature test checks (layout, accessibility, responsive) | docs | Arjun | 2 h | Documented in README |
| 33 | Write the bonus README section (purpose, implementation, trade-offs, AI concept mapping, innovation note) | docs | Yasmine | 3 h | All six qualification items present |
| 34 | Take screenshots and record a short GIF | docs | Yasmine | 2 h | Files in images/ |
| 35 | Finish README: project story, setup, reflection on design trade-offs | docs | Both | 3 h | Matches the real final project |
| 36 | Clean up file names and organization, then review commit history | docs | Arjun | 1 h | Commits are meaningful |

Checkpoint at end of Day 14: the project is complete and submittable.

## Buffer Days 15-17: Polish only

No major new features. Use these days for:

| # | Card | Label | Owner | Est. | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 37 | Fix bugs found in QA | bug | Whoever found it | as needed | Re-tested and closed |
| 38 | Apply peer-feedback fixes | content | Both | 4 h | Each fix linked to a commit |
| 39 | Final read-through of all text for typos | content | Yasmine | 1 h | No spelling errors |
| 40 | Rehearse the presentation; each person explains their own part of the code | docs | Both | 3 h | Both can answer questions on their area |
| 41 | Final push, tag the release and test a fresh clone | docs | Arjun | 1 h | Site opens correctly from a clean download |

## Status snapshot (copy and update at each standup)

| Phase | Cards | Done | In Progress | Review / QA | Blocked |
| --- | --- | --- | --- | --- | --- |
| 1. Plan + Structure | 9 | 0 | 0 | 0 | 0 |
| 2. Layout + Components | 8 | 0 | 0 | 0 | 0 |
| 3. Styling + Motion | 9 | 0 | 0 | 0 | 0 |
| 4. QA + Portfolio | 10 | 0 | 0 | 0 | 0 |
| Buffer | 5 | 0 | 0 | 0 | 0 |

## Quick standup template

Hold a 10-minute check-in each work session:

- What did I finish since last time?

- What am I working on next?

- What is blocking me?

## Risks and what to do about them

| Risk | Warning sign | Response |
| --- | --- | --- |
| A team member goes quiet | No commits or card movement for two sessions | Reassign their cards and tell the instructor early |
| Scope creep | New features appear after Day 11 | Move them to a "Later" list; do not build them |
| Merge conflicts | Two people edit styles.css at once | Work in separate branches and merge small changes often |
| Last-minute QA | Testing cards still in Backlog on Day 12 | Cut polish cards, never testing or documentation cards |
| Code you cannot explain | A teammate cannot describe their own section | Do a walkthrough together before the presentation |

## Tips for a realistic pace

- Plan about two to three focused hours of work per person per session; the hour estimates above assume that.

- Reserve the buffer days for surprises. If you finish early, use them for extra testing, not new features.

- Keep the board honest. A card is Done only when the definition of done is met and a teammate has checked it.